PELICAN CONDOMINIUM CONSTRUCTION SCHEDULE REVISED 9/09/20 2020 BUILDING RESTORATION PROJECT

BUILDING B

|  | 06 STACK | PLAN START | DURATION | PLAN END | 03 STACK | PLAN START | DURATION | PLAN END |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rail Removal/Coating Removal |  |  |  | Rail Removal/Coating Removal |  |  |  |  |
|  | Hardwall Install |  |  |  | Hardwall Install |  |  |  |  |
|  | Concrete Repair & SGD Removal | 6/22/2020 | 65 | 9/25/2020 | Concrete Repair & SGD Removal | 9/3/2020 | 15 | 9/23/2020 |  |
|  | Waterproofing Under SGD | 9/28/2020 | 3 | 9/30/2020 | Waterproofing Under SGD | 9/24/2020 | 3 | 9/28/2020 |  |
|  | SGD Install | 10/1/2020 | 10 | 10/14/2020 | SGD Install | 9/29/2020 | 5 | 10/5/2020 |  |
|  | Stucco / Painting | 10/15/2020 | 20 | 11/11/2020 | Stucco / Painting | 9/24/2020 | 15 | 10/14/2020 |  |
|  | Deck Coating | 11/12/2020 | 7 | 11/20/2020 | Deck Coating | 10/15/2020 | 5 | 10/21/2020 |  |
|  | Rail Install | 11/23/2020 | 5 | 11/27/2020 | Rail Install | 10/22/2020 | 2 | 10/23/2020 |  |
|  | Punch-out / Moving staging | 11/30/2020 | 3 | 12/2/2020 | Punch-out / Moving staging | 10/26/2020 | 3 | 10/28/2020 |  |
|  | 05 STACK | PLAN START | DURATION | PLAN END | 02 STACK | PLAN START | DURATION | PLAN END |  |
|  | Rail Removal/Coating Removal |  |  |  | Rail Removal/Coating Removal | 9/1/2020 | 10 | 9/15/2020 |  |
|  | Hardwall Install |  |  |  | Hardwall Install | 9/1/2020 | 10 | 9/15/2020 |  |
|  | Concrete Repair & SGD Removal |  |  |  | Concrete Repair & SGD Removal | 9/16/2020 | 15 | 10/6/2020 |  |
|  | Waterproofing Under SGD |  |  |  | Waterproofing Under SGD | 10/7/2020 | 3 | 10/9/2020 |  |
|  | SGD Install |  |  |  | SGD Install | 10/12/2020 | 5 | 10/16/2020 |  |
|  | Stucco / Painting |  |  | 9/17/2020 | Stucco / Painting | 10/19/2020 | 15 | 11/6/2020 |  |
|  | Deck Coating | 9/21/2020 | 5 | 9/25/2020 | Deck Coating | 11/9/2020 | 5 | 11/13/2020 |  |
|  | Rail Install | 9/28/2020 | 2 | 9/29/2020 | Rail Install | 11/16/2020 | 2 | 11/17/2020 |  |
|  | Punch-out / Moving staging | 9/29/2020 | 3 | 10/1/2020 | Punch-out / Moving staging | 11/18/2020 | 3 | 11/20/2020 |  |
|  | 04 STACK | PLAN START | DURATION | PLAN END | 01 STACK | PLAN START | DURATION | PLAN END |  |
|  | Rail Removal/Coating Removal |  |  |  | Rail Removal/Coating Removal | 10/2/2020 | 10 | 10/15/2020 |  |
|  | Hardwall Install |  |  |  | Hardwall Install | 10/2/2020 | 10 | 10/15/2020 |  |
|  | Concrete Repair & SGD Removal |  |  |  | Concrete Repair & SGD Removal | 10/16/2020 | 15 | 11/5/2020 |  |
|  | Waterproofing Under SGD |  |  |  | Waterproofing Under SGD | 11/6/2020 | 3 | 11/10/2020 |  |
|  | SGD Install | 9/3/2020 | 7 | 9/11/2020 | SGD Install | 11/11/2020 | 5 | 11/17/2020 |  |
|  | Stucco / Painting | 9/14/2020 | 15 | 10/2/2020 | Stucco / Painting | 11/18/2020 | 15 | 12/9/2020 |  |
|  | Deck Coating | 10/5/2020 | 5 | 10/9/2020 | Deck Coating | 12/10/2020 | 5 | 12/16/2020 |  |
|  | Rail Install | 10/12/2020 | 2 | 10/13/2020 | Rail Install | 12/17/2020 | 2 | 12/18/2020 |  |
|  | Punch-out / Moving staging | 10/14/2020 | 3 | 10/16/2020 | Punch-out / Moving staging | 12/21/2020 | 3 | 12/23/2020 |  |